## DBS Project Plan
Milestones | Start Date | End Date | No. Of Working Days | Resources | Comments
Project Phase - POC Activity | 2018-03-12 | 2018-04-20 | 30
Understanding the environment and application sessions with Testing SME | 2018-03-12 | 2018-03-16 | 5 | 3
Knowledge Acquisition - Sessions with application SMEs and Users | 2018-03-19 | 2018-03-23 | 5 | 3
Gap Analysis Report & Walkthrough | 2018-03-26 | 2018-03-30 | 5 | 3
POC Prep | 2018-04-02 | 2018-04-16 | 11 | 3 | The POC Preparation is delayed because of on boarding resource in DBS Hyderabad
Optimization/Recommendation Presentation | 2018-04-16 | 2018-04-16 | 1 | 3
Output Finalization | 2018-04-17 | 2018-04-18 | 2 | 3
Due Diligence Report Walkthrough | 2018-04-19 | 2018-04-19 | 1 | 3
Due Diligence Report Sign Off | 2018-04-20 | 2018-04-20 | 1 | 3
Project Phase - Phase 1 Automation Planning | 2018-04-23 | 2018-05-31 | 29
HK Setup in DBS Hyderabad | 2018-04-23 | 2018-04-27 | 5 | 2
Resource Onboarding | 2018-04-30 | 2018-05-31 | 24 | 2
System & Automation Tool Setup | 2018-04-30 | 2018-05-31 | 24 | 2
QMetry Framework Study | 2018-05-15 | 2018-05-26 | 9 | 2
Project Phase - Phase 1- M1 | 2018-06-01 | 2018-06-30 | 21
Customize QMetry Framework | 2018-06-01 | 2018-06-07 | 5 | 8
Integration of Test Management Tool (Integration with Existing DBS projects) | 2018-06-08 | 2018-06-11 | 2 | 8
Define the Automation Process | 2018-06-12 | 2018-06-12 | 1 | 8
Test Script Reusability (SG Created or Existing DBS) | 2018-06-13 | 2018-06-15 | 3 | 8
Test Plan Creation | 2018-06-18 | 2018-06-20 | 3 | 8
Test Environment Setup ( Script Automation) | 2018-06-19 | 2018-06-22 | 4 | 8
System Access to Test Environment | 2018-06-20 | 2018-06-22 | 3 | 8
Test Data Analysis | 2018-06-25 | 2018-06-30 | 5 | 8
Knowledge Session - FPS | 2018-06-25 | 2018-06-30 | 5 | 8
Project Phase - Phase 1- M2 | 2018-07-01 | 2018-07-31 | 22
System Test Script Creation | 2018-07-02 | 2018-07-31 | 22 | 8
Test Data Creation | 2018-07-02 | 2018-07-31 | 22 | 8
Test Script Review | 2018-07-16 | 2018-07-27 | 10 | 8
Rework on Test Script Created | 2018-07-18 | 2018-07-31 | 10 | 8
Test Script Validation | 2018-07-24 | 2018-07-31 | 6 | 8
Project Phase - Phase 1- M3 | 2018-08-01 | 2018-08-31 | 22
Test Data Creation | 2018-08-01 | 2018-08-31 | 22 | 8
Test Script Execution | 2018-08-01 | 2018-08-31 | 22 | 8
Rework on Failure Test Script (If required) | 2018-08-07 | 2018-08-17 | 8 | 8
Defect Management(Creation to Closure) | 2018-08-01 | 2018-08-31 | 22 | 8
Test Completion Report (TSR) | 2018-08-27 | 2018-08-31 | 5 | 8
Project Phase - Phase 1- M4 | 2018-09-01 | 2018-09-30 | 20
Continous Test Script Execution (QA , UAT Environments) | 2018-09-01 | 2018-09-28 | 20 | 8
Defect Management(Creation to Closure) | 2018-09-01 | 2018-09-28 | 20 | 8
Test Completion Report (TSR) | 2018-09-23 | 2018-09-28 | 5 | 8
Scripts Handover to FPS Team | 2018-09-28 | 2018-09-28 | 1 | 8
Customize Framework for CBS for Phase2 | 2018-09-10 | 2018-09-14 | 5 | 8
Framework Rollout for CBS Automation for Phase2 | 2018-09-23 | 2018-09-28 | 5 | 8
Project Phase - Phase 2-H1 - CBS | 2018-10-01 | 2018-12-30 | 65
Analyze the CBS application for Automation | 2018-10-01 | 2018-10-05 | 5 | 8 | Resource count will change based on the scope of automation
Knowledge Session - To automate CBS system in H1 Quarter | 2018-10-08 | 2018-10-12 | 5 | 8
Test Plan Creation | 2018-10-15 | 2018-10-19 | 5 | 8
Test Environment Setup ( Script Automation) | 2018-10-16 | 2018-10-19 | 4 | 8
System Access to Test Environment | 2018-10-15 | 2018-10-19 | 5 | 8
Test Script Creation | 2018-10-15 | 2018-11-30 | 35 | 8
Test Data Creation | 2018-10-15 | 2018-11-30 | 35 | 8
Test Script Review | 2018-11-01 | 2018-11-30 | 22 | 8
Test Script Validation | 2018-11-01 | 2018-11-30 | 22 | 8
Test Script Execution | 2018-12-03 | 2018-12-14 | 10 | 8
Continuous Test Script Execution (QA, UAT Environments) | 2018-12-17 | 2018-12-25 | 7 | 8
Test Completion Report | 2018-12-26 | 2018-12-31 | 4 | 8
Scripts Handover to CBS Team | 2018-12-31 | 2018-12-31 | 1 | 8
Project Phase - Phase 2-H2 - CBS | 2019-01-01 | 2019-03-30 | 63
Analyze the CBS application for Automation | 2019-01-01 | 2019-01-07 | 5 | 8 | Resource count will change based on the scope of automation
Knowledge Session - To automate CBS system in H1 Quarter | 2019-01-08 | 2019-01-15 | 5 | 8
Test Plan Creation | 2019-01-16 | 2019-01-22 | 5 | 8
Test Environment Setup ( Script Automation) | 2019-01-16 | 2019-01-22 | 5 | 8
System Access to Test Environment | 2019-01-16 | 2019-01-22 | 5 | 8
Test Script Creation | 2019-01-23 | 2019-02-25 | 24 | 8
Test Data Creation | 2019-01-23 | 2019-02-25 | 24 | 8
Test Script Review | 2019-02-11 | 2019-02-28 | 14 | 8
Test Script Validation | 2019-02-18 | 2019-02-28 | 9 | 8
Test Script Execution | 2019-03-01 | 2019-03-15 | 11 | 8
Continuous Test Script Execution (QA, UAT Environments) | 2019-03-18 | 2019-03-29 | 10 | 8
Test Completion Report | 2019-03-25 | 2019-03-29 | 5 | 8
Scripts Handover to CBS Team | 2019-03-29 | 2019-03-29 | 1 | 8
Project Phase - Phase 2-H3-CBS | 2019-04-01 | 2019-06-30 | 65
Analyze the CBS application for Automation | 2019-04-01 | 2019-04-05 | 5 | 8 | Resource count will change based on the scope of automation
Knowledge Session - To automate CBS system in H1 Quarter | 2019-04-08 | 2019-04-12 | 5 | 8
Test Plan Creation | 2019-04-15 | 2019-04-19 | 5 | 8
Test Environment Setup ( Script Automation) | 2019-04-15 | 2019-04-19 | 5 | 8
System Access to Test Environment | 2019-04-15 | 2019-04-19 | 5 | 8
Test Script Creation | 2019-04-22 | 2019-05-31 | 30 | 8
Test Data Creation | 2019-04-22 | 2019-05-31 | 30 | 8
Test Script Review | 2019-05-02 | 2019-05-31 | 22 | 8
Test Script Validation | 2019-05-20 | 2019-05-31 | 10 | 8
Test Script Execution | 2019-06-03 | 2019-06-14 | 10 | 8
Continuous Test Script Execution (QA, UAT Environments) | 2019-06-17 | 2019-06-28 | 10 | 8
Test Completion Report | 2019-06-24 | 2019-06-28 | 5 | 8
Scripts Handover to CBS Team | 2019-06-28 | 2019-06-28 | 1 | 8
Formulas:
No. Of Working Days = NETWORKDAYS([Start Date],[End Date],Sheet3!$A2:A139)

## Sheet3 (hidden)
Holidays
2018-03-17
2018-03-18
2018-03-24
2018-03-25
2018-03-31
2018-04-01
2018-04-07
2018-04-08
2018-03-31
2018-04-14
2018-04-15
2018-04-21
2018-04-22
2018-04-28
2018-04-29
2018-05-05
2018-05-06
2018-05-12
2018-05-13
2018-05-19
2018-05-20
2018-05-26
2018-05-27
2018-06-02
2018-06-03
2018-06-09
2018-06-10
2018-06-16
2018-06-17
2018-06-23
2018-06-24
2018-06-30
2018-07-01
2018-07-07
2018-07-08
2018-07-14
2018-07-15
2018-07-21
2018-07-22
2018-07-28
2018-07-29
2018-08-04
2018-08-05
2018-08-11
2018-08-12
2018-08-18
2018-08-19
2018-08-25
2018-08-26
2018-09-01
2018-09-02
2018-09-08
2018-09-09
2018-09-15
2018-09-16
2018-09-22
2018-09-23
2018-09-29
2018-09-30
2018-10-06
2018-10-07
2018-10-13
2018-10-14
2018-10-20
2018-10-21
2018-10-27
2018-10-28
2018-11-03
2018-11-04
2018-11-10
2018-11-11
2018-11-17
2018-11-18
2018-11-24
2018-11-25
2018-12-01
2018-12-02
2018-12-08
2018-12-09
2018-12-15
2018-12-16
2018-12-22
2018-12-23
2018-12-29
2018-12-30
2019-01-05
2019-01-06
2019-01-12
2019-01-13
2019-01-19
2019-01-20
2019-01-26
2019-01-27
2019-02-02
2019-02-03
2019-02-09
2019-02-10
2019-02-16
2019-02-17
2019-02-23
2019-02-24
2019-03-02
2019-03-03
2019-03-09
2019-03-10
2019-03-16
2019-03-17
2019-03-23
2019-03-24
2019-03-30
2019-03-31
2019-04-06
2019-04-07
2019-04-13
2019-04-14
2019-04-20
2019-04-21
2019-04-27
2019-04-28
2019-05-04
2019-05-05
2019-05-11
2019-05-12
2019-05-18
2019-05-19
2019-05-25
2019-05-26
2019-06-01
2019-06-02
2019-06-08
2019-06-09
2019-06-15
2019-06-16
2019-06-22
2019-06-23
2019-06-29
2019-06-30
2018-08-15
2019-01-14
2019-05-01